# Statement of Work — Loyalty Program Implementation for CairoMart Retail Group

# 1. Introduction and Background

This Statement of Work (SOW) is entered into between LoyaltyCo (the Provider) and CairoMart Retail Group (the Merchant) for the implementation of a points-based customer loyalty program across the Merchant's retail network.

CairoMart operates 5 retail branches in Greater Cairo and seeks to launch a unified loyalty program to increase repeat purchases and customer retention.

# 2. Objectives

Launch a fully operational loyalty points program across all 5 CairoMart branches.

Enable customers to earn 10 points for every 1 USD spent in-store.

Provide the Merchant with 20 configurable promotional offers at launch.

Achieve go-live no later than 1 December 2026.

# 3. Scope of Work

The Provider will deliver: merchant onboarding, loyalty platform configuration, API integration with the Merchant's point-of-sale (POS) system, offer setup, staff training, and go-live support.

Out of scope: hardware procurement, POS replacement, and marketing campaign design.

# 4. Commercial Requirements

The Merchant will launch 20 loyalty offers at go-live, distributed across product categories as agreed with the Account Manager.

Pricing follows the standard LoyaltyCo revenue-share model: 2.5% of the value of each redeemed offer.

The commercial contract must be countersigned before any technical integration work begins.

| Item | Quantity | Notes |
| --- | --- | --- |
| Participating branches | 5 | All Greater Cairo locations |
| Launch offers | 20 | Configured before go-live |
| Merchant onboarding questionnaires | 15 | Commercial team to collect |
| Offer configuration questionnaires | 10 | One per offer family |

# 5. Technical Requirements

The Provider will implement a REST API integration between the LoyaltyCo platform and the Merchant's POS system for real-time points accrual.

Points calculation rule: customers earn 10 points for every 1 USD spent. Points expire 12 months after accrual.

Authentication between systems uses OAuth 2.0 client-credentials flow.

The API must sustain 50 transactions per second at peak with p95 latency under 300 ms.

All API integration work, including end-to-end testing, must be completed before the go-live date.

# 6. Operations Requirements

Operations will configure the merchant account, the 5 branches, and all 20 offers in the production environment after technical validation passes.

Merchant onboarding includes collection of branch data, staff rosters, and offer approval sign-off from the Merchant's commercial representative.

# 7. Training

On-ground training is required for cashier and floor staff at each of the 5 branches. Training duration is 2 days in total, delivered by the Operations team in the week before go-live.

# 8. Milestones and Timeline

The project runs from contract signature to go-live per the schedule below.

| Milestone | Date | Owner |
| --- | --- | --- |
| Contract countersigned | 2026-10-01 | Commercial |
| Technical integration complete | 2026-11-10 | Technical |
| End-to-end testing complete | 2026-11-20 | Technical |
| Merchant configuration complete | 2026-11-24 | Operations |
| Staff training complete | 2026-11-27 | Operations |
| Go-live | 2026-12-01 | All teams |

# 9. Team and Responsibilities

The Provider assigns a cross-functional team of 8 people to this project.

| Role | Team | Responsibility |
| --- | --- | --- |
| Account Manager | Commercial | Merchant relationship, offer sign-off |
| Commercial Manager | Commercial | Contract and pricing |
| Technical Lead | Technical | Integration architecture |
| Backend Engineer | Technical | API development |
| QA Engineer | Technical | Testing and validation |
| Operations Manager | Operations | Configuration and go-live |
| Merchant Success Specialist | Operations | Onboarding and training |
| Support Agent | Operations | Post-go-live support |

# 10. Service Level Agreements

Platform availability: 99.5% monthly uptime.

Support response time: 4 business hours for priority incidents during the first 30 days after go-live.

# 11. Acceptance Criteria

The project is accepted when: all 20 offers are live in production, points accrue correctly at 10 points per 1 USD in all 5 branches, end-to-end tests pass, staff training is complete, and the Merchant signs the go-live checklist.